## Vision_Canvas
		High Level Vision Canvas
Project Name

Inspirations (note what is it inspiring)	Genre (ex: 3rd Person)	Core Pillars (in the form "User can...")	Core Systems (ex: Save/Load or Combat)	User Experience (the emotion elicited)

	IP/World (high level descriptions)

				User Types (prioritized)

## Example_of_a_Vision_Canvas
		High Level Vision Canvas
Fallout3

Inspirations (note what is it inspiring)	Genre (ex: 3rd Person)	Core Pillars (in the form "User can...")	Core Systems (ex: Save/Load or Combat)	User Experience (the emotion elicited)
- Mad Max (setting)	- First Person	- Player has to feel they are in a post-apocalyptic US	- Combat includes both ranged	- Immersion in a world destroyed
- Terminator (future setting)	- Post-apocalypse RPG	destroyed by nukes.	and melee weapons
- The Postman (setting)				- Empowerment via combat and
- Skyrim (UI)		- Players must be able to explore vast areas, both	- Exploration over vast areas	exploration leading to advancement.
		interior and exteriors
			- Progression and Changing classes	- Challenged by new interactions
		- Player can create (customize) their own character		even as the player gets more powerful.
	IP/World (high level descriptions)	with various class choices and skills.	- Narrative driven missions and
	-True to it's predecessor		character interactions.	- Player's actions matter
	while going from isometric	- Players must advance in skills and become more
	to first person	powerful in combat.		Player Types
	- Located in the United States			- Min/Maxer: Let me build out my
	- Tie to the fallen US Gov.	- Players will face enemies of various factions		character the way I want.
		including mutated creatures created by the nuclear
		war.		- Actor: A player that wants to be a key
				mover in another world.
		- Player will find conspiracies and faction supported
		storylines.		- Explorer: Give me a vast area to
				find interesting characters, easter eggs
		- Player will follow Sub story lines should exist to		and locations.
		provide more info about the world, the main character
		character and the overall goal.		- Savior: Let me be the key to changing
				the world through my actions.

## Feature_List_Example,_Template
Example Feature List:

Reference #	Feature Name	Top Level Description	Priority	Difficulty	Time To Implement	Risk	Comments
F001	Melee Combat	Primary combat system	High	High	High	Animations require modifications to the animation system
					Camera system needs to pan relative to the attack type
					VFX needs to differ for each weapon (may impact schedule)

F002	Quadripeds	We want to support enemies with 4 legs	High	High	High	The volume of animations	We may be able to use the regular system and fake it

F003	Clouds	Add moving clouds to the sky dome	Low	Moderate	High	New system	Nice to have if possible
					Players may expect weather

F004	Cover	Ability to hide behind objects	Med	Med	Med	Objects need to be of certain heights, specs need to be created	Would make the combat system more interesting
					May add complexity to the combat swings

## Tech_Design_Examples,_Template
Ver 1.1	Modified 9/11/2018
Ref #	System Name	Feature Supported	Feature Specifics	Priority	Difficulty	Risk	Time Estimation	Comments
F001	Traversal
F001a		Camera		High	Med	Low
			View Frustum					To Be determined
			Viewing Distance (Scale)					Based on Frustrum
F001b		Controls		Med	Low	Low		Timing based on Environmental layout
			Walk
			Run
			Jump
			Crouch
F001c		Determine Player Location		Low	Low	Low

F002	Melee Combat
F002a		Camera		High	Med	Med
			Over the Shoulder
F002b		Controls		High	Med	Low
			Thrust
			Swing
			Counter
			Block

F003	Enemy AI
F003a		Senses		Med	Med	Med		Based on Environment, layout and gameplay style
			Hearing
			Sight
			Speaking
F003b		Movement		Med	High	High		Environmental Dependencies
			By Class
F003c		Melee Attack		High	High	High
			By Class

F004	Enemy Spawning
F004a		Spawner Types		Med	Med	Med		Environmental Dependencies
			Based on Class
F004b		Spawner Activation		Med	Med	Med		Environmental Dependencies
			Based on Player location
F004c		Enemy Wave System		Med	Med	Med		Environmental Dependencies
			Number of waves
			Timing of waves
			Constitution of waves

F005	Enemy Death
F005a		Clean up		Med	Low	Low		Based on Design Balance
			Remove body
			Drop loot
			Reward system

F006	Reward System
F006a		Determine loot		Med	Med	Med		Based on Design Balance
			based on Player Level
F006b		Drop loot		Med	Med	Med		Based on Design Balance
			Determine Location

F007	UI					Needs to wait until we see some elements of the design
F007a		In Game Notification		Low	Low	Low
F007b		Item Notification		Med	Med	Med
F007c		Controls
			Action Activation	Low	Low	Low
F007d		Game Functions
			Exit Mission	Low	Low	Low
			Quit Game	Low	Low	Low
			Save Game	Low	Low	Low

## Milestones_Example,_Template
Project:	Your Project name goes here
Date	Milestone	Task	Assets to be created	% Complete	Comments
1/30/2019	Design
		Create Vision Canvas	None
		Create Tone Target	None
		Create Art Spectrum	None
2/15/2019	Design II
		Create Tech Design Doc	None
		Create Feature List	None
	Feature I
		Ex: Inital Play Area layout	Example: Initial UI elements
			Initial Contact Interface
			Initial Movement System, etc
Insert New Dates	Insert new Milestones	Insert New Tasks	Insert New Asset Lists		Add new rows to include new milestones, add as many as you need

Some Date	Vertical Slice				First attempt at showing what game play and look will be

## QA_Test_Plan_Example,_Template
QA Test Plan		Project:_____________________________
Date	Build #	Tester Name
1/14/2019
Test #	Unit/Feature	Item	Success/Fail
1	Main Screen
1a		Game Loads properly to Main Screen
1b		UI elements change focus correctly
1c		Choosing <Start Game> functions correctly by placing the player in the game at the beginning of the first element
1d		Choosing <Exit Game> functions correctly closing out the game cleanly and places the player back in the platform interface
1e		Choosing <Load Saved Game> functions correctly takes the player to the <Save/Load Game system
1f		Choosing <Settings> functions correctly by taking you to the Player Setting System

2	Performance
2a		Game loading time is within spec (loads within XX seconds)
2b		General game play shows no hitching or graphic errors
3	Save Game
3a		Game save time is within spec (saves within XX seconds)
3b		Saved Game can be reloaded immediately
3c		Saved Game Data is correct on reloading

	Game Play